## Workplan
Workplan |  | Application Identifier: |  | 2024/CEI/#### | Project Title: | The Point Littoral Rainforest Regeneration
Project Outcomes
No. | Outcome | Description
1 | Restoration of Littoral Rainforest | By implementing weed control and bush regeneration techniques, the threat of weeds can be managed and reduced, improving the ecological integrity and resilience of the Littoral Rainforest vegetation community.
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Establish Site Monitoring |  | 2025-03-03 | 2025-09-01 | 1
| No. | Activities
| 1 | Groundtruth mapped extent of Littoral Rainforest vegetation community and identify key target areas (i.e. worst impacted by weeds)
| 2 | Establish monitoring photo points, collect photos and survey current state of flora (i.e. develop species list recording native and weed abundance, diversity and cover)
No. | Milestone |  | Start | Finish | Outcome IDs
2 | Primary Weeding |  | 2025-09-02 | 2026-03-31 | 2
| No. | Activities
| 1 | Undertake primary weeding of priority weeds (Bitou Bush, Lantana, Trad, Cape Ivy and Passionflower) using manual, mechanical, and chemical methods, following best practice industry standards
| 2 | Collect monitoring photos at established photo points and write progress report detailing actions taken and including site maps and monitoring photos
No. | Milestone |  | Start | Finish | Outcome IDs
3 | Secondary Weeding and Revegetation |  | 2026-04-01 | 2027-12-01 | 3
| No. | Activities
| 1 | Undertake secondary weeding of priority weeds (Bitou Bush, Lantana, Trad, Cape Ivy and Passionflower) using manual, mechanical, and chemical methods, following best practice industry standards
| 2 | Plant 2000 native tubestock of selected species and maintain to ensure establishment and survival of >90%
| 3 | Collect monitoring photos at established photo points and write progress report detailing actions taken and including site maps and monitoring photos
Project Measures
No. | Milestone
1 | Maintenance
| No. | Activities | Activity Type
| 1 | Undertake secondary weeding of priority weeds (Bitou Bush, Lantana, Trad, Cape Ivy and Passionflower) using manual, mechanical, and chemical methods, following best practice industry standards | Weeding
|  |  | Measure | Expected Output | Unit
|  |  | Area Weeded | 231000 | Square metres
|  |  | Reduction in weed cover (%) | 50 | Percentage
| No. | Activities | Activity Type
| 2 | Plant 2000 native tubestock of selected species and maintain to ensure establishment and survival of >90% | Planting
|  |  | Measure | Expected Output | Unit
|  |  | Area revegetated | 2310 | Square metres
|  |  | Number of Plantings | 2000 | Number
|  |  | Different Species planted | 15 | Number
|  |  | Survival rate of plantings (%) | 90 | Percentage
| No. | Activities | Activity Type
| 3 | Collect monitoring photos at established photo points and write progress report detailing actions taken and including site maps and monitoring photos | Regeneration
|  |  | Measure | Expected Output | Unit
|  |  | Area regenerating | 231000 | Square metres
Project Budget |  | Selected Ratio: | 2:1
|  |  |  | Whole Total: | 67600 | 0 | 22533 | 45067
No | Milestone
1 | Establish Site Monitoring
| No | Activities |  | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Groundtruth mapped extent of Littoral Rainforest vegetation community and identify key target areas (i.e. worst impacted by weeds) |  |  | 1300 | 0 | 433 | 867
| 2 | Establish monitoring photo points, collect photos and survey current state of flora (i.e. develop species list recording native and weed abundance, diversity and cover) |  |  | 1300 | 0 | 433 | 867
|  |  |  | Total: | 2600 | 0 | 866 | 1734
No | Milestone
2 | Primary Weeding
| No | Activities |  | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Undertake primary weeding of priority weeds (Bitou Bush, Lantana, Trad, Cape Ivy and Passionflower) using manual, mechanical, and chemical methods, following best practice industry standards |  |  | 30550 | 0 | 10183 | 20367
| 2 | Collect monitoring photos at established photo points and write progress report detailing actions taken and including site maps and monitoring photos |  |  | 650 | 0 | 217 | 433
|  |  |  | Total: | 31200 | 0 | 10400 | 20800
No | Milestone
3 | Secondary Weeding and Revegetation
| No | Activities |  | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Undertake secondary weeding of priority weeds (Bitou Bush, Lantana, Trad, Cape Ivy and Passionflower) using manual, mechanical, and chemical methods, following best practice industry standards |  |  | 26000 | 0 | 8667 | 17333
| 2 | Plant 2000 native tubestock of selected species and maintain to ensure establishment and survival of >90% |  |  | 7150 | 0 | 2383 | 4767
| 3 | Collect monitoring photos at established photo points and write progress report detailing actions taken and including site maps and monitoring photos |  |  | 650 | 0 | 217 | 433
|  |  |  | Total: | 33800 | 0 | 11267 | 22533