## Workplan
Workplan |  | Application Identifier: | 2024/CEMP/#### | Project Title: | Main Creek Estuary Scoping Study
Project Outcomes
No. | Outcome | Description
1 | Scoping Study complete | A completed Scoping Study for Main Creek Estuary and catchments, with a forward program for remaining stages of the CMP.
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Draft Scoping Study |  | 2025-03-03 | 2026-01-31 | 1
| No. | Activities
| 1 | Data compilation, literature review, stakeholder / community liaison,
| 2 | Site assessment and initial field work
| 3 | Draft scoping study produced
| 4 | Presentation to committee
No. | Milestone |  | Start | Finish | Outcome IDs
2 | Final Scoping Study |  | 2026-02-03 | 2026-07-21 | 2
| No. | Activities
| 1 | Deliver final scoping study
| 2 | Presentation to committee
Project Measures
No. | Milestone
1 | Final Scoping Study
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Deliver final scoping study | Scoping impact / identifying the risk | Cost benefit analysis/distribution analysis completed | no | Yes/No
|  |  |  | Investigation/design completed | no | Yes/No
|  |  |  | Properties covered by a Coastal Management Program | 0 | Number
|  |  |  | At risk locations that coastal hazard adaptation strategies been identified | 0 | Number
|  |  |  | Coastal Management Program certified | no | Yes/No
|  |  |  | Estuaries covered by a Coastal Management Program | 0 | Number
|  |  |  | Scoping study finalised | yes | Yes/No
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Presentation to committee | Consulting and collaborating | People participating in community consultations | 100 | Number
|  |  |  | Committee / steering committee meetings / workshops | 2 | Number
|  |  |  | Public meetings / workshops | 2 | Number
Project Budget |  | Funding Ratio: | 2:1
|  |  | Project Total: | 45000 | 0 | 15001 | 29999
No | Milestone
1 | Draft Scoping Study
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Data compilation, literature review, stakeholder / community liaison, |  | 10000 | 0 | 3333 | 6667
| 2 | Site assessment and initial field work |  | 5000 | 0 | 1667 | 3333
| 3 | Draft scoping study produced |  | 5000 | 0 | 1667 | 3333
| 4 | Presentation to committee |  | 5000 | 0 | 1667 | 3333
|  |  | Total: | 25000 | 0 | 8334 | 16666
No | Milestone
2 | Final Scoping Study
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Deliver final scoping study |  | 15000 | 0 | 5000 | 10000
| 2 | Presentation to committee |  | 5000 | 0 | 1667 | 3333
|  |  | Total: | 20000 | 0 | 6667 | 13333